## timelog.csv
Benjamin
Feature | Subject | Hours | Comment
Activity stream | Activity Stream | 1.5 | Minifying activity stream.
Activity stream | Activity Stream | 0.5 | Fixing bug with incorrectly displayed comments.
Activity stream | Activity Stream | 3 | Making comments more generic
Activity stream | Activity Stream | 18 | Notification system, comments, re-structuring all current objects to extend from one base class, needed for notifications.
Activity stream | Return key should work on write comment field. | 0.5 | Return key sends comment comment field now.
Activity stream | Adding several more notifications to be displayed in the notification stream. | 0.5 | Had to improve some stuff in the notifcations logging process in order to make the permission check working for ratings and comments.
Activity stream | Adding several more notifications to be displayed in the notification stream. | 2 | Adding several more notifications, we should have notifications for everything now.
Activity stream | Adding several more notifications to be displayed in the notification stream. | 3 | I added several new notifications for documents, pages and fragments.
29
Avatar uploader | avatar uplodader | 5 | Makes avatar uploader working.
5
Barcode | create barcode | 7 | The barcodes are now using real case-related data. There was a lot of re-structuring necessary, in order to make this working fluently.
Barcode | create barcode | 8.5 | Generating barcodes in SVG format based on test data.
15.5
Documentation | Setting up new git repository for documentation | 0.5 | Repository available at https://github.com/benoertel/unplagged-documentation
Documentation | Create papers, broschures, nametags, presentation for showtime. | 7 | Printing all the stuff at dbusiness and kopierladen
Documentation | Create papers, broschures, nametags, presentation for showtime. | 4.5 | Creating impress presentation
Documentation | Create papers, broschures, nametags, presentation for showtime. | 15.5 | Technology poster, General poster, nametags, some improvements on the broschur
Documentation | Create papers, broschures, nametags, presentation for showtime. | 6 | I crated a nametag layout, a first draft of the trifold broschure and an A0 logo file.
Documentation | impress.js Showtime presentation | 5 | Working at the impress presentation for the Showtime
Documentation | impress.js Showtime presentation | 5.5 | Working at the impress presentation for the Showtime
Documentation | Documentation version 2 | 4 | Writing at chapter barcode, fragments and plagaware.
Documentation | Documentation version 2 | 3 | Writing at chapter fragments and activity stream.
Documentation | Documentation version 2 | 1 | Meeting for documentation version 2.
Documentation | Documentation version 2 | 2.5 | Writing at chapter activity stream
Documentation | Documentation version 2 | 1 | Creating timelog sheet
Documentation | Documentation version 2 | 3 | Writing chapter roles and permissions
Documentation | Documentation version 2 | 0.5 | Proof reading
59
Documents | Implementing Sim-Text in PHP based on the Javascript version | 2 | Some refactoring of the simtext code into the appropriate directories and minor modifications.
Documents | Parsing mulitple-page documents should be possible | 3 | Cron job setup on server.
Documents | Parsing mulitple-page documents should be possible | 5 | Identifying issues with wrong bit depth of imagemagick output files, updating parser to work with multiple pages, identifying and fixing local problem with imagemagick not parsing pdfs properly
Documents | Plagiarism detection not working anymore. | 1 | The response page is now added to the acl of allowed actions for guests and the input params are not choked anymore.
Documents | "Select all" for checkboxes in dehyphen area. | 0.5 | Changed style for selecting/ unselecting all lines in a page.
Documents | "Select all" for checkboxes in dehyphen area. | 1.5 | Beautifying dehyphen form
Documents | Remove bibtex from and new document option from fragment form | 1 | BibTex field was removed from fragment form and moved to document form.
Documents | Save pages in single lines | 16 | Saving pages in single lines, modifying simtext to support the new page model with single lines.
Documents | Parsing of .txt files | 1 | Txt files can be parsed now.
Documents | Optimizing the storage of BibTex information | 7.5 | Several improvements for the bibtex part of the application.
Documents | Documents can be crated by hand as well | 1 | Documents can be added through a form and not through parsing only.
39.5
Files | Downloading files and viewing images not working anymore | 2 | Fixing but with file downloads
2
Fragments | A user can create a fragment by hand | 0.5 | Fixing bug where hidden bibtex information did not stay hidden when the form was displayed with errors after a submit.
Fragments | A user can create a fragment by hand | 2.5 | Adds option for editing a fragment and restructures the edit/creation process.
Fragments | A user can create a fragment by hand | 4 | A user can choose from existing documents or create a new one during fragment creation, many improvements in the interface.
Fragments | A user can create a fragment by hand | 4.5 | Adding bibtex information to fragment, implementing the single fragment page view with plagiarism text and source text, several changes to the internal fragment structure.
Fragments | A user can create a fragment by hand | 4 | Initial fragment model structure
Fragments | A user can select a fragment by selecting a part of an ocr scanned document | 2 | A user can select a part of the document page and then create a fragment
Fragments | A user can select a fragment by selecting a part of an ocr scanned document | 3.5 | Trying to fix a problem with fragment deletion when deleting a page.
Fragments | A user can approve/decline a fragment | 3.5 | The ratings are now in the conversation stream as well.
Fragments | A user can approve/decline a fragment | 4 | Basic fragment approval/decline implementation
Fragments | determine document/fragment per case | 3 | Fragments, reports and documents are now case-related.
Fragments | Fragment page - move note information to the bottom | 0.25 | Moves fragment note information to the bottom
Fragments | Make fragment creation from text selection working again | 2 | Creating fragments from text selection is working again based on the new line-based storing mechanism.
Fragments | Two-column fragment creation | 2.5 | Adding button to page/show page to switch between single and two-column view for fragment creation, making document selection possible.
Fragments | Two-column fragment creation | 4 | Updating contextmenu and javascript for fragment creation in order to handle to documents and prefill the fragment form for both sides (candidate and source).
Fragments | Two-column fragment creation | 6 | Creating a two column view whih enables paging on two documents at the same time.
Fragments | Pages and fragments can not edited | 9 | Versionable items can now be edited without a optimistic lock exception.
Fragments | Add required ratings field to case / lock fragments | 4.5 | Automatic locking of fragments that reached a pre-defined amount of approvals.
59.75
Meeting | Debbie Meeting 11.04.2012 | 1
Meeting | Meeting 12.04.12 | 2
Meeting | Team Meeting â€“ 2012-04-16 | 3.5
Meeting | Skype Meeting 20.04.12 | 2
Meeting | Team Meeting 23.04.12 | 3
Meeting | Skype Meeting 29.04.12 | 2
Meeting | Debbie Meeting 30.04.12 | 2 | Debbie Meeting
Meeting | Skype Meeting 3.05.12 | 1.3
Meeting | Meeting 2012-05-07 | 3 | Meeting 2012-05-07
Meeting | Skype Meeting 28.05.12 | 1.2
Meeting | Skype Meeting 31.05.12 | 1
Meeting | "Debbie Meeting" 01.06.12 | 1
Meeting | Meeting 2012-06-11 | 1.5
Meeting | Meeting 2012-06-29 | 2
Meeting | Skype Meeting Showtime Vorbereitung | 1 | Skype Meeting
Meeting | Meeting Showtime Preperation | 2.25
Meeting | meeting 12.07.2012 - preparation for showtime (cont.) | 4 | Preperation showtime.
Meeting | meeting 11.07.2012 - preparation for showtime | 3
Meeting | Showtime | 9 | Showtime
Meeting |  | 1.5 | Showtime Orga Meeting
Meeting | Debbie Meeting 2012-05-14 | 1.5
48.75
Reports | Create simtext report cron and report page | 5 | Creating cron job the Zend way, creating report list page
Reports | Starting detection report not working | 0.5 | Fixes bug where user account was removed when startin a plagiarism detection.
Reports | Improvement of reports | 4.5 | Some bug fixes
Reports |  | 4 | Figuring out a problem where the report creation was not working anymore.
Reports |  | 5 | Refactoring simtext report page.
19
Rights and roles | Add collaborator selection to case form | 4.5 | Collaborators can be added/removed from a case.
Rights and roles | Finalizing the rights ACL | 6.5 | ACL Testing, cloning user roles when creating a new case.
Rights and roles | Finalizing the rights ACL | 11 | Considering inheritanted permissions in ACL, finalizing permission edit form for rights on single objects.
Rights and roles | Finalizing the rights ACL | 10 | Implementing permission checks in the entire application, creating form for authorizing users for a single object.
Rights and roles | Finalizing the rights ACL | 7 | Discussing process of permission checking on single objects, implementing permission checks for objects selected in list views.
Rights and roles |  | 5.5 | Fixing some bugs in the role management.
44.5
System architecture | Fix Postfix mail sending on server | 3 | Figuring out problems with postfix not sending mails.
System architecture | Centralising overall properties in the base model | 1 | Moving created attribute to base model and removing it and its getters/setters from all other objects.
System architecture | Any object can be versionable | 4.5 | Figuring out why new versions were not saved.
System architecture | Any object can be versionable | 5
System architecture | Any object can be versionable | 8
System architecture | Create cronjob | 0.5 | I moved the crons to the scripts/jobs directory and updated the crontab file.
System architecture | Make command line build scripts working in any environment | 1.5 | Any of our build scripts is accepting a parameter for the environment now
System architecture | Move setTarget() from file controller to the case controller | 1.5 | The target is now defined in the case and is set on a document instead of a file.
System architecture | Make actions and states editable | 3.5 | Adding forms for editing states and actions, adding list view
System architecture | Determining memory leak in file parsing process | 8.5 | Fixing memory leak in file parsing process
System architecture | Removing php shorttags | 0.5 | Fixed bug with php shorttags.
37.5
Tags | Add tags | 6 | Creating a generic form element for adding tags using autocompletion.
Tags | Add tags | 3 | Investigations concerning using own viewScripts on form elements properly.
9
Testing | Error: Class Application_Model_State has no field or association named isRemoved | 0.5 | Fixing bug where actions and states list views didn't work anymore.
Testing |  | 3 | Some overall testing on the website.
Testing |  | 3 | General testing, closing tickets, writing mails and other project management stuff.
6.5
User | Implement password recovery | 2 | Adding a 24 hour lock for password recovery requests of a single account.
User | Implement password recovery | 2 | A user can request a password recovery mail and then follow a link to change it.
User | Implement account removal | 2 | A user can remove the own account and all data associated with it.
User | Account verification link is not accessible | 0.5
User | Send username in password-recovery mail in the mail text | 0.25
User | Password recovery and account verification page not accessible for guests | 0.5 | Added 'user_verify' and 'user_recover-password' to the initpermissions script and re-created the guest role on the staging server.
7.25
User Interface | Improve create/edit forms | 2 | Improving process for cases (adds editing cases option), documents (adds editing documents option) and fragments.
User Interface | Combine actions in tables | 1 | I added the dropdown to documents and fragments list view and put the whole menu into an own partial.
User Interface | More responsive toolbar | 1.5 | Makes user-menu responsive.
User Interface | Match all styles to all templates | 5 | Modifying styles of all page-related action sites.
User Interface | Aktuelles und Kontroverses unbenennen | 0.5 | Removes aktuelles und kontroverses from home page sidebar, adds latest cases to sidebar.
User Interface | Make header background image higher (and wider) | 0.5 | Adds beta patch as own element, wider and higher header bg image.
User Interface | Make tables responsive | 2 | All tables are responsive now.
User Interface | Improvements of user interface and bug-fixing | 2 | Making tables responsive.
User Interface | Improvements of user interface and bug-fixing | 0.5 | Adding pagination to document page detail view
User Interface | Improvements of user interface and bug-fixing | 0.5 | Avoiding direct output of html in parsed documents.
User Interface | Improvements of user interface and bug-fixing | 1 | Refactoring document list page.
User Interface | Improvements of user interface and bug-fixing | 2 | Uploading test documents, testing crons.
User Interface | Improvements of user interface and bug-fixing | 1 | Fixing issues in changelog views, creating new abstract controller that offers changelog behavior
User Interface | Improvements of user interface and bug-fixing | 0.5 | Adding new notifications at several places.
User Interface | Improvements of user interface and bug-fixing | 1 | Several small improvements to UI, testing on mobile devices as well.
User Interface | Integrating Twitter Bootstrap | 1 | Making actions button and dropdown menu right aligned in all list views.
User Interface | Integrating Twitter Bootstrap | 2.5 | Making contextmenu using bootstrap.
User Interface | Integrating Twitter Bootstrap | 1.5 | Updating all buttons in the application to use bootstrap css, cleaning up styles.css.
User Interface | Integrating Twitter Bootstrap | 2 | Integrating progress bar for cron tasks.
User Interface | Adding pagination to all page views | 1.5 | Pagination is now available to all page-related sites.
User Interface | Replace right side actions by a fixed collapsable menu at the right. | 1 | Some CSS fixes on the right side menu.
User Interface | Replace right side actions by a fixed collapsable menu at the right. | 6 | Making the actions menu hanging fixed at the right side and adapting the css.
User Interface | Fork me on Github Ribbon | 0.25 | Replacing the beta patch with a 'fork me on github' ribbon.
User Interface | Add red asterisk to required form fields | 0.5 | Adds red asterisk to required form fields
User Interface | Add missing translation to language file | 3 | Added several more translations.
User Interface | Add missing translation to language file | 2.5 | Adding several translations to the language file.
User Interface | Add language selection before parsing files. | 1.5 | Add language selection before parsing files.
User Interface |  | 3 | Beautifying actions menu, testing.
User Interface |  | 1.5 | Fixing some css bugs.
User Interface |  | 4 | Improving workflows on the page and css bug fixing (Setting the target document, making form css more cross-browser compatible)
52.75
435
1305